## Sheet1
Requirement ID | Requirement Description | Story points | Priority | Sprint No.
1 | Create Repository and setup Jira/ GitHub integration | 1 | 1 | 1
2 | Implement Spotify OAuth 2.0 login to authenticate users without creating new accounts | 13 | 1 | 1
3 | Fetch user's username from Spotify | 2 | 1 | 1
4 | Fetch user profile picture from Spotify | 2 | 1 | 1
5 | Fetch user listening history data from Spotify | 3 | 1
6 | Setup database to store Spotify data | 3 | 1 | 1
7 | Establish connection to cloud database on app launch | 8 | 1
8 | On Spotify connection failure, display error message | 3 | 1
9 | On database connection failure, display error message | 3 | 1
10 | Fetch all users' usernames from Spotify database | 2 | 1
11 | Fetch all users' profile pictures from Spotify database | 2 | 1
12 | Fetch all users' listening history data from Spotify database | 2 | 1
13 | Store user's username in cloud database | 3 | 1
14 | Store user profile picture in cloud database | 3 | 1
15 | Store user listening history data in cloud database | 3 | 1
16 | After logging in, show the logged-in user's dashboard by default | 3 | 1
17 | On application launch, display a log-in with Spotify landing page | 5 | 1
18 | Create user dashboard layout and page to display relevant data | 5 | 1
19 | Display user's username on user's dashboard | 2 | 1 | 1
20 | Display user's profile picture on user's dashboard | 2 | 1 | 1
21 | Display user's listening history on user's dashboard | 3 | 1
22 | Derive formula to calculate diversity score based on genres listened to | 5 | 2
23 | Calculate a diversity score per user on the user's listening history using derived formula | 3 | 2
24 | Derive formula to calculate a music taste rating based on the average of a series of listening histories | 5 | 2
25 | Calculate a music taste rating per user based on Team 25's listening histories using the derived formula | 3 | 2
26 | Display user's diversity score on user's dashboard | 2 | 2
27 | Display user's music taste rating on user's dashboard | 2 | 2
28 | Display a global leaderboard of all active users | 5 | 3
29 | Option to filter leaderboard by diversity score | 3 | 4
30 | Option to filter leaderboard by music taste rating | 3 | 4
31 | On selection of a user from the leaderboard, display that user's dashboard | 5 | 4
32 | Add an about page with useful data for the user | 3 | 4
33 | Explain diversity score formula on about page | 1 | 4
34 | Explain music taste rating formula on about page | 1 | 4
35 | Display a song of the day as a banner on the website | 3 | 5
36 | Display the song of the day's title on the song of the day banner | 2 | 5
37 | Display the song of the day's album art on the song of the day banner | 2 | 5
38 | Display the song of the day's author on the song of the day banner | 2 | 5
39 | Select the song of the day randomly from one of Team 25's listening histories. Ignore song duplicates. | 3 | 5