## Sheet1
Requirement ID | Requirement Description | Story points | Priority | Sprint No. | Status
1 | Create Repository and setup Jira/Github integration | 1 | 1 | 1 | Complete. Respository is setup as demonstrated by the submission link
2 | Implement Spotify OAuth 2.0 login to authenticate users without creating new accounts | 13 | 1 | 1 | Complete. Users click the login button (see Figure 2) and are taken to Spotify's OAuth login screen (See Figure 4). Spotify's authentication and authroization servers then post a callback to our application and we redirect the user to their Scorify dashboard (See Figures 1 and 3).
3 | Fetch user's username from Spotify | 2 | 1 | 1 | Complete. We fetch the user's username from Spotify. See Figure 1.
4 | Fetch user profile picture from Spotify | 3 | 1 | 1 | Complete. We fetch the user's profile picture from Spotify. See Figure 1.
6 | Setup database to store Spotify data | 3 | 1 | 1 | Complete. We now have a database server setup remotely that is accessible for this project. See dbconnection/postgresql_info.md in GitHub (Figure 5).
16 | After logging in, show the logged-in user's dashboard by default | 3 | 1 | 1 | Complete. On log-in, it shows the logged-in user's dashboard. See Figure 1.
17 | On application launch, display a log-in with Spotify landing page | 5 | 1 | 1 | Complete. When the application is launched, by default it shows the login with Spotify landing page. See Figure 2.
19 | Display user's username on user's dashboard | 2 | 1 | 1 | Complete. We display the user's username on their dashboard. See Figure 1.
20 | Display user's profile picture on user's dashboard | 2 | 1 | 1 | Complete. We display the user's profile picture on their dashboard. See Figure 1.
22 | Derive formula to calculate diversity score based on genres listened to | 5 | 2 | 1 | Complete. See the initial architecture overview document. Also see Figure 6.
24 | Derive formula to calculate a music taste rating based on the average of a series of listening histories | 5 | 2 | 1 | Complete. See the initial architecture overview document. Also see Figure 7.
Figure 3. The loading screen while fetching data from Spotify.
Figure 1. The current dashboard page.
Figure 4. Spotify's authorization service's sign-in page.
Figure 2. The login page.
Figure 5. The database connection information.
Figure 6. The genre diversity score formula.
Figure 7. The music taste rating score formula.